## Development Budget
BUILDING BLUEPRINT
Custom Home Development Budget Template
Your Project Name Here
PROJECT INFORMATION
Property Address: |  |  | Enter your property address
Prepared For: |  |  | Your name
Anticipated Start Date: |  |  | Target construction start
Construction Period (months): | 18 |  | Typical range: 12-24 months depending on complexity
KEY PROJECT ASSUMPTIONS
Target Square Footage: | 3000 |  | Conditioned living space (not including garage, unfinished basement)
Construction Cost per SF: | 500 |  | RULE OF THUMB: $350-500/SF basic custom, $500-700 mid-range, $700-1000+ high-end
Calculated Hard Costs: | 1500000
Category / Line Item | Estimated Cost | % of Total | Notes & Building Blueprint Rules of Thumb
I. ACQUISITION & PRE-DEVELOPMENT
Land Acquisition | 550000 |  | RULE OF THUMB: Land should be 10-20% of total project cost. If land exceeds 25%, reconsider project feasibility.
Legal Fees (Acquisition) | 5000 |  | Title review, contract negotiation, closing representation. Budget $3,000-8,000.
Legal Fees (Zoning/Planning) | 3000 |  | Variance applications, planning board hearings. Can escalate significantly with contested approvals.
Survey (Boundary & Topographic) | 4500 |  | ESSENTIAL. Never skip. Budget $3,000-6,000. Topo survey required for site design.
Title Insurance & Fees | 10000 |  | Typically 0.5-1% of purchase price. Negotiate—often inflated.
Building Permit (% of hard costs) | 1% |  | INPUT AS DECIMAL. Check with your municipality—ranges from 0.5% to 2% of construction value.
Building Permit (Calculated) | 15000 |  | Auto-calculated from percentage above.
Phase I Environmental | 4000 |  | Required by most lenders. Budget $2,500-5,000. Skip at your own risk on previously developed land.
Geotechnical / Soil Borings | 6000 |  | CRITICAL for foundation design. Don't skip—soil surprises are expensive. $4,000-10,000.
Zoning / ARB / Historic Review Fees | 2500 |  | Application fees vary widely. Historic districts can add significant cost & time.
SUBTOTAL: ACQUISITION & PRE-DEV | 600000.01
II. SITE DEVELOPMENT & UTILITIES
Demolition (Existing Structures) | 15000 |  | Mobile homes $5-15K, houses $15-40K. Asbestos/lead abatement can double costs.
Tree Removal & Stump Grinding | 7500 |  | Large trees $1,000-3,000 each. Clear only what's necessary—mature trees add value.
Excavation (Foundation) | 25000 |  | RULE OF THUMB: $8-15/SF of footprint. Basements add significant cost.
Rock Removal / Blasting Allowance | 15000 |  | HIGH RISK LINE ITEM. Can be $0 or $100K+. Geotech report is your friend here.
Foundation Excavation & Prep | 10000 |  | Over-excavation, compaction, gravel base. Often underestimated.
Temporary Access Road & Staging | 4000 |  | Gravel drive, laydown area. Essential for material delivery.
Temporary Power & Water | 5000 |  | Temp poles, meters. Some utilities charge substantial hookup fees.
Erosion & Sediment Control | 4000 |  | Silt fence, inlet protection. Required by code—don't skip or you'll get fined.
Rough Site Grading | 4000 |  | Initial grading for drainage and construction access.
Retaining Walls (Allowance) | 15000 |  | Highly variable. Engineered walls $50-150/face SF. Boulder walls cheaper.
Stormwater / Drainage System | 12000 |  | Dry wells, French drains, swales. Undersizing = wet basement forever.
Utility Hookup: Sewer | 5000 |  | Connection fees vary wildly by municipality. $2,000-20,000 range.
Utility Hookup: Water | 5000 |  | Tap fees + trenching. Well alternative often $15,000-30,000.
Utility Hookup: Electric | 5000 |  | Service drop, trenching, panel. 200A minimum for modern homes.
Utility Hookup: Communications | 2500 |  | Conduit for fiber/cable. Run extra conduit—it's cheap insurance.
SUBTOTAL: SITE DEV & UTILITIES | 134000
III. HARD COSTS – NEW CONSTRUCTION
Note: Line items below are for detailed tracking. Default is the lump sum calculated above.
RULE OF THUMB: Hard costs typically represent 50-60% of total project budget.
A. SITE CONCRETE |  |  | Foundation, footings, slabs. RULE OF THUMB: $15-25/SF of footprint for standard foundation.
Footings | 0 |  | Continuous footings for walls, isolated footings for point loads.
Foundation Walls | 0 |  | Poured concrete or block. Poured typically stronger and more waterproof.
Slabs (Basement & Garage) | 0 |  | 4" slab on grade typical. Consider radiant heat rough-in.
Waterproofing & Foundation Drains | 0 |  | Don't cheap out. Basement waterproofing failures are catastrophic and expensive to fix.
B. FRAMING |  |  | RULE OF THUMB: $25-45/SF for wood frame. Steel framing 20-30% premium.
Lumber & Framing Labor | 0 |  | Lumber prices volatile. Lock in pricing when possible.
Sheathing & Subfloor | 0 |  | ZIP system or traditional sheathing + WRB. ZIP costs more but saves labor.
Hardware & Connectors | 0 |  | Simpson ties, hangers, hold-downs. Required by code.
C. EXTERIOR ENVELOPE |  |  | Roofing, siding, windows. RULE OF THUMB: $35-60/SF of exterior surface.
Roofing | 0 |  | Asphalt shingles $5-8/SF, standing seam metal $12-20/SF, slate $25-50/SF.
Siding / Cladding | 0 |  | Fiber cement $8-15/SF installed, wood $12-20/SF, stone veneer $25-40/SF.
Exterior Insulation / WRB | 0 |  | Continuous insulation increasingly code-required. Budget $3-8/SF.
Gutters & Downspouts | 0 |  | Seamless aluminum $8-12/LF, copper $25-40/LF.
D. WINDOWS & DOORS |  |  | MAJOR COST DRIVER. Can range from $30K to $200K+ on same house.
Windows & Sliding Doors | 0 |  | Budget $500-2,500 per window depending on quality. Large sliders $5,000-15,000 each.
Exterior Doors & Hardware | 0 |  | Entry doors $1,500-10,000. Good hardware matters.
Garage Doors | 0 |  | Insulated steel $1,500-3,000, custom wood $5,000-15,000.
E. ROUGH MEP (Mechanical/Electrical/Plumbing) |  |  | RULE OF THUMB: $50-80/SF total for all MEP rough-in.
Rough Plumbing | 0 |  | Main lines, vents, fixture rough-in. More bathrooms = more cost.
Rough HVAC | 0 |  | Ductwork, refrigerant lines, equipment pads. Mini-splits often cheaper than ducted.
Rough Electrical & Low Voltage | 0 |  | 200A service minimum. Budget for EV charger, smart home rough-in.
F. INSULATION & DRYWALL |  |  | RULE OF THUMB: $8-15/SF for insulation, $4-8/SF for drywall.
Insulation (Thermal & Sound) | 0 |  | Spray foam $2-4/SF, batts $1-2/SF. Spray foam air seals too.
Drywall Hang & Tape | 0 |  | Level 4 finish standard, Level 5 for large walls with critical lighting.
G. INTERIOR FINISHES |  |  | HIGHLY VARIABLE. This is where budgets explode. Set firm allowances.
Flooring (Wood, Tile, Carpet) | 0 |  | Hardwood $8-20/SF installed, tile $10-25/SF, carpet $5-12/SF.
Millwork, Trim, Cabinetry | 0 |  | IKEA cabinets $200-400/LF, semi-custom $500-1,000/LF, custom $1,000-2,500/LF.
Stairs & Railings | 0 |  | Standard wood stairs $5-10K, custom steel/glass $20-50K.
Painting | 0 |  | Interior $2-4/SF. Premium paints worth the upcharge for durability.
H. FIXTURES & APPLIANCES |  |  | Set FIRM allowances. Scope creep here is real.
Plumbing Fixtures | 0 |  | Toilets $300-2,000, faucets $200-1,500, tubs $500-10,000.
Lighting Fixtures | 0 |  | Budget $5,000-15,000 minimum for a custom home. Can easily hit $50K.
Appliances (Kitchen & Laundry) | 0 |  | Mid-range package $10-20K, high-end $30-80K.
Fireplace / Wood Stove | 0 |  | Gas fireplace $5-12K installed, wood stove $3-8K, masonry fireplace $15-30K.
I. GC OVERHEAD & PROFIT (if using GC) |  |  | RULE OF THUMB: 15-25% of hard costs. Negotiate but expect to pay fair value.
General Conditions | 0 |  | Dumpsters, toilets, temp fencing, supervision. Typically 5-8% of hard costs.
GC Overhead | 0 |  | Office, insurance, staff. Typically 5-10% of hard costs.
GC Profit | 0 |  | Typically 5-10% of hard costs. Risk premium for fixed-price contracts.
SUBTOTAL: HARD COSTS (Use Calculated or Detail) | 1500000 |  | Uses calculated hard cost from SF × $/SF. Override if using detailed line items.
IV. SOFT COSTS & FINANCING
RULE OF THUMB: Soft costs typically run 15-25% of hard construction costs.
Architect Fee (%) | 12% |  | RULE OF THUMB: 8-15% of hard costs for full services. Lower for production homes, higher for complex custom.
Architect Fee (Calculated) | 0 |  | Auto-calculated. Negotiate phased payments tied to deliverables.
Structural Engineer (%) | 2% |  | Typically 1-3% of hard costs. Complex structures (steel, cantilevers) at higher end.
Structural Engineer (Calculated) | 0 |  | Auto-calculated.
Civil Engineer / Site Plan | 8000 |  | Site plan, grading plan, stormwater design. $5,000-15,000 typical.
Survey (As-Built) | 1500 |  | Required for C of O. Confirms structure matches approved plans.
Interior Designer | 35000 |  | Optional but valuable. Can save money through trade discounts. Fees vary widely.
Landscape Architect | 8000 |  | Planting plan, hardscape design. Can be bundled with architect or separate.
Lighting Designer | 4500 |  | Worth it for custom homes. Prevents expensive fixture mistakes.
Energy Modeling / HERS / Blower Door | 2500 |  | Required in many jurisdictions. HERS rating increasingly important for resale.
Construction Loan Interest | 0 |  | See Interest Calculator sheet. RULE OF THUMB: Budget 3-5% of loan amount.
Loan Origination Fees | 5000 |  | Typically 0.5-1.5% of loan amount. Negotiate hard.
Lender Legal Fees | 2000 |  | Lender's attorney fees—you pay them. Budget $1,500-3,000.
Appraisal & Inspections | 3000 |  | Initial appraisal + draw inspections (typically 4-6 during construction).
Builder's Risk Insurance | 15000 |  | RULE OF THUMB: 1-1.5% of hard costs annually. Required by lender.
SUBTOTAL: SOFT COSTS | 84500
V. POST-CONSTRUCTION & CARRY COSTS
Landscaping & Hardscaping | 20000 |  | RULE OF THUMB: Budget 5-10% of home value for mature landscaping. $20-50K typical for basic.
Final Site Grading | 3000 |  | Topsoil, seeding, finish grading after construction traffic.
Property Taxes (Year 1 - Pre-Build) | 10000 |  | Current taxes on unimproved land. Verify with assessor.
Property Taxes (Year 2 - Post-Build) | 35000 |  | EXPECT SIGNIFICANT INCREASE. Assessor will reassess after C of O.
Homeowners Insurance (Annual) | 3500 |  | Get quotes early. Custom homes can be harder to insure.
Window Treatments | 15000 |  | Often forgotten in budgets. Basic shades $10-20K, motorized $30K+.
Move-In / Final Cleaning | 10000 |  | Final clean, punch list items, furniture moves, misc.
SUBTOTAL: POST-CONSTRUCTION | 96500
VI. PROJECT TOTALS
Total Project Cost (Before Contingency) | 2415000.01
Total Cost per Square Foot | 805 |  | BENCHMARK: All-in cost $600-900/SF typical for custom, $900-1,200+ for high-end.
VII. CONTINGENCY
RULE OF THUMB: Total contingency should be 10-20% of project cost. Underfunded contingency = project failure.
Hard Cost Contingency (%) | 15% |  | MINIMUM 10-15%. Unknown conditions, design changes, price escalation.
Hard Cost Contingency ($) | 0 |  | Auto-calculated.
Site Development Contingency (%) | 20% |  | HIGHER at 15-20%. Site work has most unknowns—rock, water, soil issues.
Site Development Contingency ($) | 0 |  | Auto-calculated.
Soft Cost Contingency (%) | 5% |  | 5-10% typical. Design fees, permit delays, inspection failures.
Soft Cost Contingency ($) | 0 |  | Auto-calculated.
TOTAL CONTINGENCY | 0
TOTAL PROJECT COST WITH CONTINGENCY | 2415000.01
VIII. BUDGET HEALTH CHECK
Land as % of Total | 22.77% |  | Target: 10-20%. Over 25% signals potential feasibility issues.
Hard Costs as % of Total | 62.11% |  | Target: 50-60%. Primary driver of overall budget.
Soft Costs as % of Hard Costs | 5.633% |  | Target: 15-25%. Higher for complex/custom projects.
Contingency as % of Total | 0% |  | Target: 10-15%. Under 10% is risky.

## Interest Calculator
CONSTRUCTION LOAN INTEREST CALCULATOR
LOAN ASSUMPTIONS
Annual Interest Rate: | 7% |  | Current construction rates typically 7-9%
Total Facility Amount: | 500000 |  | Total loan commitment (not all drawn at once)
Term (Months): | 24 |  | Typical: 12-24 months. Match to construction schedule + buffer.
DRAW SCHEDULE
RULE OF THUMB: Interest is calculated on outstanding principal only. Front-load draws = more interest.
Month | Draw Amount | Cumulative Principal | Monthly Interest
1 | 100000 | 100000 | 583.3333
2 | 0 | 100000 | 583.3333
3 | 50000 | 150000 | 875
4 | 0 | 150000 | 875
5 | 0 | 150000 | 875
6 | 50000 | 200000 | 1166.6667
7 | 0 | 200000 | 1166.6667
8 | 0 | 200000 | 1166.6667
9 | 50000 | 250000 | 1458.3333
10 | 0 | 250000 | 1458.3333
11 | 0 | 250000 | 1458.3333
12 | 50000 | 300000 | 1750
13 | 0 | 300000 | 1750
14 | 0 | 300000 | 1750
15 | 50000 | 350000 | 2041.6667
16 | 0 | 350000 | 2041.6667
17 | 0 | 350000 | 2041.6667
18 | 50000 | 400000 | 2333.3333
19 | 0 | 400000 | 2333.3333
20 | 0 | 400000 | 2333.3333
21 | 50000 | 450000 | 2625
22 | 0 | 450000 | 2625
23 | 0 | 450000 | 2625
24 | 50000 | 500000 | 2916.6667
TOTAL INTEREST |  |  | 40833.3333
Maximum Principal Outstanding |  |  | 500000

## Rules of Thumb
BUILDING BLUEPRINT - RULES OF THUMB
BUDGET ALLOCATION BENCHMARKS
Category | Target % | Notes
Land Acquisition | 10-20% | If land exceeds 25% of total project cost, re-evaluate feasibility
Hard Construction Costs | 50-60% | Core building costs should be the dominant budget category
Soft Costs | 15-25% | Architecture, engineering, permits, financing costs
Site Development | 5-10% | Can be much higher with challenging sites (rock, slope, access issues)
Contingency | 10-15% | NEVER budget less than 10%. 15-20% for unknowns is prudent
CONSTRUCTION COST BENCHMARKS
Quality Level | $/SF Range | Description
Basic Custom | $350-500 | Standard finishes, production-level specifications
Mid-Range Custom | $500-700 | Upgraded finishes, some custom elements, architect-designed
High-End Custom | $700-1,000 | Premium finishes, full custom design, high-performance systems
Luxury/Ultra-Custom | $1,000+ | No-compromise finishes, exotic materials, complex engineering
PROFESSIONAL FEES BENCHMARKS
Professional | % of Hard Costs | Notes
Architect (Full Services) | 8-15% | Schematic through CA. Production homes lower, complex custom higher
Structural Engineer | 1-3% | Higher for steel frames, complex cantilevers, seismic zones
Civil Engineer | Flat fee $5-15K | Site plan, grading, stormwater. Larger sites cost more
Interior Designer | 10-20% of FF&E | Or hourly $150-500/hr. Trade discounts often offset fees
GC Overhead + Profit | 15-25% | Includes general conditions (5-8%), overhead (5-10%), profit (5-10%)
RED FLAGS & WARNING SIGNS
⚠ Land cost exceeds 25% of total project budget
⚠ Contingency budgeted at less than 10%
⚠ No geotechnical report before finalizing budget
⚠ Construction loan term doesn't include 3-6 month buffer
⚠ Allowances not specified for fixtures, appliances, finishes
⚠ No builder's risk insurance budgeted
⚠ Permit costs not verified with local building department
⚠ Utility hookup costs not confirmed with providers
⚠ No budget for survey (boundary AND topographic)
⚠ Site development costs estimated without site visit