Design Phase Gate Checklist

Use this checklist at each design phase transition to confirm all critical decisions are locked before moving forward. Changes become exponentially more expensive as design progresses — catching gaps early saves significant money and time.

Project Title: _________________________________________________

Date: _________________________________________________

Cost of Change Reference

Schematic Design: ~5% of design fee to change | Design Development: ~15-25% | Construction Documents: ~50%+ | Construction: 5-10x the original design cost

Schematic Design (SD) Gate

| Item | Complete (Y/N) | Notes/Concerns |
| --- | --- | --- |
| Floor plan layout approved |  |  |
| Overall building footprint and massing confirmed |  |  |
| Number of stories and ceiling heights established |  |  |
| Primary material palette identified |  |  |
| Preliminary budget alignment confirmed with cost estimator |  |  |
| Site placement and orientation finalized |  |  |
| Key views and spatial relationships defined |  |  |
| Preliminary energy/performance strategy outlined |  |  |
| Ready to proceed? ☐ Yes ☐ No |  | List open items: |

Design Development (DD) Gate

| Item | Complete (Y/N) | Notes/Concerns |
| --- | --- | --- |
| All rooms dimensioned and confirmed |  |  |
| Structural system defined |  |  |
| MEP systems schematically designed |  |  |
| Window and door schedule preliminary |  |  |
| Interior finish palette established |  |  |
| Landscape concept integrated with architecture |  |  |
| Updated cost estimate within budget tolerance |  |  |
| All engineering disciplines coordinated |  |  |
| Lighting and AV infrastructure planned |  |  |
| Ready to proceed? ☐ Yes ☐ No |  | List open items: |

Construction Documents (CD) Gate

| Item | Complete (Y/N) | Notes/Concerns |
| --- | --- | --- |
| All drawings complete and coordinated across disciplines |  |  |
| Specifications written for all materials and systems |  |  |
| Final cost estimate reviewed and approved |  |  |
| Energy code compliance verified |  |  |
| All finish selections finalized with lead times confirmed |  |  |
| Permit submittal package assembled |  |  |
| Value engineering complete (if needed) |  |  |
| Owner sign-off on all documents |  |  |
| Ready to proceed? ☐ Yes ☐ No |  | List open items: |

Construction Administration (CA) Readiness

| Item | Complete (Y/N) | Notes/Concerns |
| --- | --- | --- |
| Permits approved or on track |  |  |
| Builder selected and contract executed |  |  |
| Architect's CA scope and fee confirmed |  |  |
| Shop drawing review process established |  |  |
| Site visit schedule agreed upon |  |  |
| RFI response protocol defined |  |  |
| Ready to proceed? ☐ Yes ☐ No |  | List open items: |

Design Phase Timeline Tracker

| Phase | Planned Start | Planned End | Actual Start | Actual End | Variance |
| --- | --- | --- | --- | --- | --- |
| Schematic Design (SD) |  |  |  |  |  |
| Design Development (DD) |  |  |  |  |  |
| Construction Documents (CD) |  |  |  |  |  |
| Construction Admin (CA) |  |  |  |  |  |

Next Steps

Use this gate checklist framework to create a transparent decision-making process with all stakeholders. It's not about saying 'no' to changes, but about understanding the cost and scheduling impact of revisions at each phase.

- Schedule gate review meetings before proceeding to each phase

- Document decisions and any deferred items with clear ownership

- Share gate status with your builder during the DD phase so they understand what drives cost

- Track timeline variance to learn from each phase for future projects