Site Mobilization & Kick-Off Checklist

Use this checklist to ensure your job site is properly set up and your project team is aligned before construction begins. A well-organized site and a clear kick-off meeting set the tone for the entire project.

Project Title: _____________________________________________________

Date: _____________________________________________________

Part 1: Site Mobilization

| Item | Status | Responsible Party | Date Complete | Cost | Notes |
| --- | --- | --- | --- | --- | --- |
| Temporary electrical service / construction power |  |  |  |  |  |
| Temporary water supply |  |  |  |  |  |
| Temporary sanitary facilities (portable toilet) |  |  |  |  |  |
| Temporary phone/internet (if remote site) |  |  |  |  |  |
| Construction entrance / access road established |  |  |  |  |  |
| Driveway or access route protected from heavy equipment |  |  |  |  |  |
| Material delivery route confirmed (truck access, turning radius) |  |  |  |  |  |
| Parking area designated for workers |  |  |  |  |  |
| Staging area designated for materials and equipment |  |  |  |  |  |
| Material storage area (protected, organized) |  |  |  |  |  |
| Dumpster/waste management positioned |  |  |  |  |  |
| Erosion and sediment controls installed (silt fence, inlet protection) |  |  |  |  |  |
| Tree and landscape protection fencing installed |  |  |  |  |  |
| Survey stakes and benchmarks set and protected |  |  |  |  |  |
| Construction fencing / perimeter secured |  |  |  |  |  |
| Safety signage posted |  |  |  |  |  |
| First aid kit on site |  |  |  |  |  |
| Emergency contact information posted |  |  |  |  |  |
| Security measures (camera, lockbox, lighting — if needed) |  |  |  |  |  |
| OSHA poster and required notices displayed |  |  |  |  |  |
| Adjacent property owners notified of construction |  |  |  |  |  |
| Working hours communicated |  |  |  |  |  |
| Contractor contact information shared for concerns |  |  |  |  |  |
| Shared access or boundary issues addressed |  |  |  |  |  |

Part 2: Project Kick-Off Meeting

Meeting Date: ________________ | Location: ________________ | Attendees: ________________

Agenda & Documentation

| Topic | Discussed | Decisions / Notes |
| --- | --- | --- |
| Project overview and design intent review |  |  |
| Contract scope review and key milestones |  |  |
| Master schedule walkthrough |  |  |
| Communication protocols (single point of contact, email vs. phone, response times) |  |  |
| Meeting cadence (weekly OAC meetings recommended) |  |  |
| Decision turnaround times (48-hour standard) |  |  |
| Change order process review |  |  |
| Payment application and draw schedule |  |  |
| Quality expectations and inspection process |  |  |
| Documentation standards (daily logs, photos, reports) |  |  |
| RFI process (how questions get asked and answered) |  |  |
| Material storage and site organization standards |  |  |
| Working hours and site access rules |  |  |
| Safety requirements and incident reporting |  |  |
| Emergency procedures and contacts |  |  |

Partnership Rules

Primary point of contact (Owner side): _____________________________________________________

Primary point of contact (Builder side): _____________________________________________________

Weekly meeting day/time: _____________________________________________________

Decision turnaround commitment: ________________ hours

Preferred communication method:  ☐ Email   ☐ Phone   ☐ Text   ☐ Project Management Software: ________________

Documentation sharing method: _____________________________________________________

Next Steps

Distribute completed kick-off meeting notes to all attendees within 48 hours. Ensure all temporary utilities are confirmed and tested before the first day of work. Schedule weekly OAC (Owner-Architect-Contractor) meetings beginning the week of project start.