Master Schedule & Long-Lead Tracker

Use this tracker to monitor your construction schedule's critical path and manage long-lead items that must be ordered well before they're needed on site. A missed order date on a 16-week window package can delay your entire project by months.

Project Title: ________________________________

Date: ________________________________

Part 1: Critical Path Milestone Monitor

| Milestone | Planned Start | Planned Finish | Actual Start | Actual Finish | Variance (Days) | Float Available | Impact Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Permits approved |  |  |  |  |  |  |  |
| Site mobilization |  |  |  |  |  |  |  |
| Excavation & foundation |  |  |  |  |  |  |  |
| Framing — structural |  |  |  |  |  |  |  |
| Roof dry-in |  |  |  |  |  |  |  |
| Window and door installation |  |  |  |  |  |  |  |
| MEP rough-in |  |  |  |  |  |  |  |
| Insulation and air sealing |  |  |  |  |  |  |  |
| Drywall |  |  |  |  |  |  |  |
| Interior trim and millwork |  |  |  |  |  |  |  |
| Cabinetry and countertops |  |  |  |  |  |  |  |
| Flooring |  |  |  |  |  |  |  |
| Final MEP trim-out |  |  |  |  |  |  |  |
| Paint and finishes |  |  |  |  |  |  |  |
| Landscaping and site work |  |  |  |  |  |  |  |
| Final inspections |  |  |  |  |  |  |  |
| Punch list |  |  |  |  |  |  |  |
| Certificate of Occupancy |  |  |  |  |  |  |  |
| Move-in |  |  |  |  |  |  |  |

Part 2: 3-Week Look-Ahead

Update this section every week during your OAC (Owner-Architect-Contractor) meeting. Focus on what's happening now and what needs to happen next — not rehashing the past.

| Week | Activity | Trade/Contractor | Status | Owner Decisions Needed | Notes |
| --- | --- | --- | --- | --- | --- |
| Week of ___ |  |  |  |  |  |
| Week of ___ |  |  |  |  |  |
| Week of ___ |  |  |  |  |  |

Part 3: Long-Lead Items Tracker

| Item | Specification Status | Vendor/Supplier | Order Date Required | Lead Time (Weeks) | Expected Delivery | Needed On-Site By | Buffer (Days) | Ordered? | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Windows (8-20 weeks) |  |  |  |  |  |  |  |  |  |
| Exterior doors (6-12 weeks) |  |  |  |  |  |  |  |  |  |
| Structural steel (6-16 weeks) |  |  |  |  |  |  |  |  |  |
| Cabinetry (8-14 weeks) |  |  |  |  |  |  |  |  |  |
| Countertops — natural stone (4-8 weeks) |  |  |  |  |  |  |  |  |  |
| Appliances (4-12 weeks) |  |  |  |  |  |  |  |  |  |
| Specialty tile (6-14 weeks) |  |  |  |  |  |  |  |  |  |
| Plumbing fixtures (4-10 weeks) |  |  |  |  |  |  |  |  |  |
| Lighting fixtures — custom (6-12 weeks) |  |  |  |  |  |  |  |  |  |
| Fireplace/insert (4-8 weeks) |  |  |  |  |  |  |  |  |  |
| Stair components — custom (6-10 weeks) |  |  |  |  |  |  |  |  |  |
| Garage doors (4-8 weeks) |  |  |  |  |  |  |  |  |  |

Red Flag: Any item with less than 2 weeks of buffer between expected delivery and on-site need date should be escalated immediately.

Next Steps

Review and update this tracker weekly during project execution. Prioritize long-lead items immediately to prevent schedule delays.